## Sheet1
Module | Description | Sent to Merge date | Server-Web-App | Merged date | Deployed date | Changelog | MR Link | Members worked on this Change/Task
Hostel Managementt | PR for hostel warden module | 2026-03-02 | APP | 2026-03-02 | 2026-04-16 | Added Hostel warden module | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/390 | Mahima Jassi P1 (Product), Nihal B P11(BE), Madari Ravalika P19(Flutter), Harsh Khatri P16 (Flutter)
Generic | Migrate Excel exports to SpreadCheetah Source Generator | 2026-03-02 | Server | 2026-03-02 | 2026-03-03 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1485 | Nithin B P10(BE), Suresh Gundupalli P15 (BE)
Design | (File Upload & Bulk Upload UI Refinements) | 2026-03-03 | Web App, Admin Panel | 2026-03-03 | 2026-03-03 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/598 | Rachamalla Sai Ram Reddy P27(FE), Manisha Shankarlal Sachdeo P23(FE)
Fee Payments | Fee Payment Legacy Check Gateway Key Addition | 2026-03-03 | Server | 2026-03-03 | 2026-03-03 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1509 | Sanjay Madari P9(BE), Chidananda Sahu P13 (BE)
Design | NcTabs component: Added scrollable support and tab switch enhancement. | 2026-03-03 | Web App, Admin Panel | 2026-03-03 | 2026-03-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/591 | Rachamalla Sai Ram Reddy P27(FE), Madineni Priyanka P26(FE)
Design | MR for redesign components enhancements and issues. | 2026-03-04 | Web App, Admin Panel | 2026-03-04 | 2026-03-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/614 | Rachamalla Sai Ram Reddy P27(FE), Harshini Bollineni P21 (FE)
Hostel Managementt | Hostel Warden module implementation | 2026-03-04 | Server | 2026-03-04 | 2026-03-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1486 | Sanjay Madari P9(BE), Santosh Sankanal P4(QA), Nihal B P11(BE)
Hostel Managementt | Hostel Warden module implementation | 2026-03-04 | Web App, Admin Panel | 2026-03-04 | 2026-03-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/585 https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/571 | Rachamalla Sai Ram Reddy P27(FE), Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Madari Ravalika P19(Flutter)
Package Upgrade | L&D: Packages upgrade and Bun migration | 2026-03-04 | Web App | 2026-03-04 | 2026-03-05 |  | https://git.narayanagroup.com/nconnect/nconnect_lnd_web/-/merge_requests/82 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Sriramula Prathyusha P20 (FE)
Package Upgrade | Bun migration and Package upgrades(Service desk) | 2026-03-05 | Web App | 2026-03-05 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/service_desk_web/-/merge_requests/114 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Sriramula Prathyusha P20 (FE)
Announcement | Enhancement: Enable/ disable push notifications for announcements | 2026-03-06 | Server | 2026-03-06 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1505 | Sanjay Madari P9(BE), Chidananda Sahu P13 (BE), G Lakshmi Priyanka P3(QA), Mrinmoyee Banerjee P6(Product Designer)
Announcement | Enhancement: Enable/ disable push notifications for announcements | 2026-03-06 | Admin Panel | 2026-03-06 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/616 | Rachamalla Sai Ram Reddy P27(FE), Sriramula Prathyusha P20 (FE), G Lakshmi Priyanka P3(QA), Mrinmoyee Banerjee P6(Product Designer)
Design | (Bulk upload enhancement) | 2026-03-10 | Web App, Admin Panel | 2026-03-10 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/619 | Rachamalla Sai Ram Reddy P27(FE), Manisha Shankarlal Sachdeo P23(FE)
HKS | Hks Security Capture Issue FIx | 2026-03-10 | Server | 2026-03-10 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1517 | Sanjay Madari P9(BE), Nihal B P11(BE)
HKS | MR for HKS feedback forms issue Fix | 2026-03-11 | Server | 2026-03-11 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1520 | Sanjay Madari P9(BE)
Adoption Calling | Adoption Calling Analytics view reports and filters issue | 2026-03-11 | Server | 2026-03-11 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1494 | Sanjay Madari P9(BE), G Lakshmi Priyanka P3(QA), Chidananda Sahu P13 (BE)
Bus Tracking | Slab and Transport amount addition in Bus Tracking Student Map view. | 2026-03-11 | Server | 2026-03-11 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1515 | Sanjay Madari P9(BE)
Bus Tracking | Slab and Transport amount addition in Bus Tracking Student Map view. | 2026-03-11 | Admin Panel | 2026-03-11 | 2026-03-11 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/592 | B Mouli P18 (FE)
Design | preset filter component | 2026-03-12 | Web App, Admin Panel | 2026-03-12 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/455 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Aditya Singh P22(FE), Harshini Bollineni P21 (FE)
Bus Tracking | Skipped fetching attachments for each bus which is not required for Bus Notes export. | 2026-03-12 | Server | 2026-03-12 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1524 | Sanjay Madari P9(BE)
Re-Design | Enh: Redesign Changes | 2026-03-13 | Admin Panel, Web App | 2026-03-13 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/620 | Rachamalla Sai Ram Reddy P27(FE), B Mouli P18 (FE), Sriramula Prathyusha P20 (FE)
Re-Design | MR to make useExport composable flexible for multiple export types. | 2026-03-13 | Admin Panel | 2026-03-13 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/623 | Santosh Sankanal P4(QA), B Mouli P18 (FE), Manisha Shankarlal Sachdeo P23(FE)
Bus Tracking | Enh: Bus Tracking Bulk Student Mapping update | 2026-03-13 | Admin Panel | 2026-03-13 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/593 | B Mouli P18 (FE)
Bus Tracking | Enh: Bus Tracking Bulk Student Mapping update | 2026-03-13 | Server | 2026-03-13 | 2026-03-16 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1528 | Sanjay Madari P9(BE), Sreedhar Patti P12(BE)
HKS | Added feedback form permissions for forms insertion | 2026-03-17 | Server | 2026-03-17 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1530 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Nihal B P11(BE)
Attandance | Moved exam attendance APIs to common controller | 2026-03-18 | Server | 2026-03-18 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1496 | G Lakshmi Priyanka P3(QA), Sanjay Madari P9(BE), Nihal B P11(BE)
HKS | Updated daily checklist form insertion time | 2026-03-18 | Server | 2026-03-18 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1534 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Santosh Sankanal P4(QA), Nihal B P11(BE)
Service Desk | Feature: Auto Login Using Cookies and Redirection to Admin Panel. | 2026-03-18 | Web App | 2026-03-18 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/service_desk_web/-/merge_requests/95 | Rachamalla Sai Ram Reddy P27(FE), Mahima Jassi P1 (Product), G Lakshmi Priyanka P3(QA), Aditya Singh P22(FE)
Bus Tracking | Updated expiry validity excel report with required fields (Fleet management) | 2026-03-18 | Server | 2026-03-18 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1531 | Sanjay Madari P9(BE), Suresh Gundupalli P15 (BE)
MicroSchedule | microschedule enable edit in single entry for reported topics can be merged. | 2026-03-18 | Admin Panel | 2026-03-18 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/607 | Rachamalla Sai Ram Reddy P27(FE), Mahima Jassi P1 (Product), G Lakshmi Priyanka P3(QA), Sriramula Prathyusha P20 (FE), Nithin B P10(BE)
Bus Tracking | changes in bus student mapping | 2026-03-18 | Admin Panel | 2026-03-18 | 2026-03-18 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/595 | B Mouli P18 (FE)
MicroSchedule | Optimized the v_microschedule view | 2026-03-24 | Server | 2026-03-24 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1537 | Nithin B P10(BE), Suresh Gundupalli P15 (BE)
Re-Design | MR for ncswitch border variant and enabling save as draft in single entry | 2026-03-24 | Admin Panel | 2026-03-24 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/634 | G Lakshmi Priyanka P3(QA), Harshini Bollineni P21 (FE)
Digital Library | Pertain to the Digital Library MIS Report generation via Hangfire and email delivery. | 2026-03-24 | Server | 2026-03-24 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1493 | "Amogh Nath P24(FE,BE)", Nithin B P10(BE)
Digital Library | Pertain to the Digital Library MIS Report generation via Hangfire and email delivery. | 2026-03-24 | Web App | 2026-03-24 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/video_feedback_web/-/merge_requests/94 | "Amogh Nath P24(FE,BE)", Nithin B P10(BE)
HKS | Staff app feedback forms building addition. | 2026-03-25 | APP | 2026-03-25 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/406 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Madari Ravalika P19(Flutter), Medagone Ranadeep P17 (Flutter), Nihal B P11(BE)
Re-Design | Enhancement: beforeLeave hook for controlled tab switching and updated the runtime script. | 2026-03-26 | Admin Panel | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/625 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Aditya Singh P22(FE)
Service Desk | Base URLs updates in env file (service desk) | 2026-03-26 | Web App | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/service_desk_web/-/merge_requests/116 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), "Amogh Nath P24(FE,BE)"
HKS | HkS module changes | 2026-03-26 | Server | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1506 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Nihal B P11(BE), Santosh Sankanal P4(QA)
HKS | HkS module changes | 2026-03-26 | Admin Panel | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/610 | Rachamalla Sai Ram Reddy P27(FE), "Amogh Nath P24(FE,BE)", Santosh Sankanal P4(QA), Mahima Jassi P1 (Product)
Bus Tracking | MR: changes in student mapping. | 2026-03-26 | Admin Panel | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/597 | Sanjay Madari P9(BE), B Mouli P18 (FE), Sreedhar Patti P12(BE)
Generic | hotfix for the MIS report generation issue | 2026-03-26 | Server | 2026-03-26 | 2026-03-26 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1540 | Sanjay Madari P9(BE), "Amogh Nath P24(FE,BE)"
Generic | Enhancement: File Upload Validation and Button loading behavior. | 2026-03-30 | Admin Panel | 2026-03-30 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/630 | Rachamalla Sai Ram Reddy P27(FE), "Amogh Nath P24(FE,BE)"
TPT | Refactor TPT module Excel Reports to Use SpreadCheetah Source Generator | 2026-03-30 | Server | 2026-03-30 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1541 | Nithin B P10(BE), Suresh Gundupalli P15 (BE)
Parent Check-In | Parent Check-In Feedback Analytics. | 2026-03-31 | Admin Panel | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/626 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Premchand Kodali P14 (BE), G Lakshmi Priyanka P3(QA)
Parent Check-In | Parent Check-In Feedback Analytics. | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1521 | Mahima Jassi P1 (Product), Rachamalla Sai Ram Reddy P27(FE), Harshini Bollineni P21 (FE), G Lakshmi Priyanka P3(QA)
Prodigy | feat: Restrict modules for prodigy students | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1539 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Santosh Sankanal P4(QA), Chidananda Sahu P13 (BE)
Adoption Calling | Adoption calling & NScribeAI audio stream Endpoint Moved to Common. | 2026-03-31 | Admin Panel | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/621 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Sriramula Prathyusha P20 (FE)
Adoption Calling | Adoption calling & NScribeAI audio stream Endpoint Moved to Common. | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1513 | Nithin B P10(BE), Sreedhar Patti P12(BE), G Lakshmi Priyanka P3(QA)
Fee Payments | feat: fee payment branch-level gateway config & encryption | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1533 | Sanjay Madari P9(BE), Chidananda Sahu P13 (BE)
Generic | Extracts GCS client creation into reusable CreateGcsClientWithServiceAccount method (was inline in upload logic) | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1543 | "Amogh Nath P24(FE,BE)"
MicroSchedule | MR for microschedule bulk upload excel columns addition | 2026-03-31 | Admin Panel | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/644 | Rachamalla Sai Ram Reddy P27(FE), Nithin B P10(BE), Harshini Bollineni P21 (FE)
GPS Dashboard | Gps Dashboard distance and trip reports enhancements | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1403 | Sanjay Madari P9(BE), Nihal B P11(BE)
nTrack | Gps Dashboard distance and trip reports enhancements | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/ntrack_server/-/merge_requests/39 | Sanjay Madari P9(BE), Nihal B P11(BE)
AY Migration | Academic year Migration | 2026-03-31 | Server | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1544 | Sanjay Madari P9(BE), Chidananda Sahu P13 (BE), Santosh Sankanal P4(QA)
AY Migration | Academic year Migration | 2026-03-31 | Admin Panel | 2026-03-31 | 2026-03-31 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/598 https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/645 | Rachamalla Sai Ram Reddy P27(FE), Santosh Sankanal P4(QA), Manisha Shankarlal Sachdeo P23(FE), Harshini Bollineni P21 (FE)
Staff App | Pr for UI and bug fixes - Staff app | 2026-03-05 | APP | 2026-03-05 | 2026-04-16 | Fixes for: MS teacher main screen loading issue. Ay behaviour not as expected in ms principal flow. Onboarding ay drop down overflow. Updated Onboarding level drop down ui. Loading not coming while logout. | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/401 | Medagone Ranadeep P17 (Flutter), Harsh Khatri P16 (Flutter)
MicroSchedule | PR for Arrow Icon state not updating in activity history screen - MS - Staff app | 2026-03-05 | APP | 2026-03-05 | 2026-04-16 | Update: In activity history single screen, the additional details expansion icon is not updating as expected. Updated it. | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/402 | Madari Ravalika P19(Flutter), Harsh Khatri P16 (Flutter)
Package Upgrade | flutter(3.41.2) and package upgrade - Parent app | 2026-03-05 | APP | 2026-03-05 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/216 | Harsh Khatri P16 (Flutter)
Package Upgrade | flutter(3.41.2) and package upgrade - Staff app | 2026-03-05 | APP | 2026-03-05 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/400 | Harsh Khatri P16 (Flutter)
Staff App | New multi select dropdown - Staff app | 2026-03-06 | APP | 2026-03-06 | 2026-04-16 | Changes: Built a reusable MultiSelectSearchDropDown widget using the multi_dropdown package. Supports multi/single select, search, select all, deselect all, and chip-based selected items. |  | Medagone Ranadeep P17 (Flutter), Harsh Khatri P16 (Flutter)
HKS | Hostel warden controller dispose fix | 2026-03-06 | APP | 2026-03-06 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/404 | Mahima Jassi P1 (Product), Harsh Khatri P16 (Flutter)
Staff App | Pr for Version bump - staff app | 2026-03-06 | APP | 2026-03-06 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/405 | Medagone Ranadeep P17 (Flutter), Harsh Khatri P16 (Flutter)
Package Upgrade | Flutter and packages upgrade of both the apps | 2026-03-18 | APP | 2026-03-18 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/219 https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/403 | Medagone Ranadeep P17 (Flutter)
Staff App | Staff app smart auth plugin terminal warning fix: | 2026-03-25 | APP | 2026-03-25 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/409 | Medagone Ranadeep P17 (Flutter)
Staff App | Staff app env file update | 2026-03-26 | APP | 2026-03-26 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/410 | Medagone Ranadeep P17 (Flutter)
Parent App | Parent app version bump and env file update: | 2026-03-26 | APP | 2026-03-26 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/220 | Medagone Ranadeep P17 (Flutter)
Parent Check-In | Added a redirection icon alongside the Received tag. On clicking, the form will open with the previously submitted responses, allowing users to review past feedback. | 2026-03-26 | APP | 2026-03-26 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/407 | Mahima Jassi P1 (Product), G Lakshmi Priyanka P3(QA), Medagone Ranadeep P17 (Flutter)
HKS | Staff app feedback forms enhancements | 2026-03-27 | APP | 2026-03-27 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/411 | Mahima Jassi P1 (Product), Medagone Ranadeep P17 (Flutter)
Staff App | Staff App packages and env update | 2026-03-30 | APP | 2026-03-30 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/412 | Madari Ravalika P19(Flutter), Medagone Ranadeep P17 (Flutter)
Parent App | Parent App packages and env update | 2026-03-30 | APP | 2026-03-30 | 2026-04-16 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/221 | Madari Ravalika P19(Flutter), Medagone Ranadeep P17 (Flutter)