## Sheet1
Module | Description | Sent to Merge date | Server-Web-App | Merged date | Deployed date | Changelog | MR Link | Members who worked on this MR
Events & Gallery | events and gallery language support | 2026-01-04 | Admin Panel | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/590 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Harshini Bollineni P21 (FE), Mrinmoyee Banerjee P6(Product Designer)
Events & Gallery | events and gallery language support | 2026-01-04 | Server | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1497 | G Lakshmi Priyanka P3(QA), Sanjay Madari P9(BE), Mrinmoyee Banerjee P6(Product Designer)
Opinion Poll | Refactor Opinion Poll module Excel Reports to Use SpreadCheetah Source Generator | 2026-01-04 | Server | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1512 | Nithin B P10(BE), Suresh Gundupalli P15 (BE)
nScribeAI | Enhancements - Added Presetfilter Added RiskFactor Filter in all APIs | 2026-01-04 | Admin Panel | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/632/ | G Lakshmi Priyanka P3(QA), M Gaurav Dhir P2(product), Sriramula Prathyusha P20 (FE)
NscribeAI | Enhancements - Added Presetfilter Added RiskFactor Filter in all APIs | 2026-01-04 | Server | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1546 | Nithin B P10(BE), M Gaurav Dhir P2(product), G Lakshmi Priyanka P3(QA)
Staff App | Allowing Notice Period Staff to access nConnect | 2026-01-04 | Server | 2026-01-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1552 | Sanjay Madari P9(BE)
HKS | HkS Analytics export report enhancement | 2026-02-04 | Server | 2026-02-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1542 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Nithin B P10(BE), Nihal B P11(BE)
Bus Tracking | Bus tracking email summary bg job issue fix | 2026-02-04 | Server | 2026-02-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1553 | Sanjay Madari P9(BE), Nihal B P11(BE)
Bus Tracking | Position aggregation service data insertion issue | 2026-02-04 | Server | 2026-02-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/ntrack_server/-/merge_requests/41 | Sanjay Madari P9(BE), Nithin B P10(BE), Nihal B P11(BE)
nTrack | adding "From" and "To" date filter in reports | 2026-02-04 | Web App | 2026-02-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/ntrack_web/-/merge_requests/47 | Sanjay Madari P9(BE), B Mouli P18 (FE)
Generic | MR for AY21 Migration fix | 2026-06-04 | Server | 2026-06-04 | 2026-06-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1556 | Sanjay Madari P9(BE), Santosh Sankanal P4(QA)
Digital Library | Updated the background logo on videos in the Digital Library. | 2026-06-04 | Web App | 2026-06-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/video_feedback_web/-/merge_requests/96 | Rachamalla Sai Ram Reddy P27(FE), Nithin B P10(BE)
HKS | HKS Enhnacements | 2026-06-04 | Server | 2026-06-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1550 | Mahima Jassi P1 (Product), Nihal B P11(BE), Sanjay Madari P9(BE)
HKS | HKS Enhnacements | 2026-06-04 | Web App | 2026-06-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/647 | Mahima Jassi P1 (Product), "Amogh Nath P24(FE,BE)", Rachamalla Sai Ram Reddy P27(FE)
HKS | HKS:- Correction in module data key | 2026-07-04 | Web App | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/hks_staff_web/-/merge_requests/32 | Mahima Jassi P1 (Product), B Mouli P18 (FE)
Fee Payments | Return error message to parent app in HDFC payment flow | 2026-07-04 | Server | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1557 | "Amogh Nath P24(FE,BE)"
Events & Gallery | fix: Board type filter in events & gallery | 2026-07-04 | Server | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1558 | Sanjay Madari P9(BE), Nihal B P11(BE)
Adoption Calling | Task: Enabled the grace period of one month in adoption calling module date selection. | 2026-07-04 | Admin Panel | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/651 | Rachamalla Sai Ram Reddy P27(FE)
HKS | fix: Hks capture count issue | 2026-07-04 | Server | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1551 | Mahima Jassi P1 (Product), Nithin B P10(BE), Nihal B P11(BE), Santosh Sankanal P4(QA)
HKS | fix: Hks capture count issue | 2026-07-04 | Web App | 2026-07-04 | 2026-08-04 |  | https://git.narayanagroup.com/nconnect/hks_staff_web/-/merge_requests/32 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), B Mouli P18 (FE)
nTrack | enhancements in the ntrack_web. | 2026-08-04 | Web App | 2026-08-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/ntrack_web/-/merge_requests/48 | Sanjay Madari P9(BE), B Mouli P18 (FE)
Announcement | Enh: Announcement Module Revamp. | 2026-09-04 | Admin Panel | 2026-09-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/642 | Rachamalla Sai Ram Reddy P27(FE), Aditya Singh P22(FE), Mahima Jassi P1 (Product), Santosh Sankanal P4(QA)
Announcement | Enh: Announcement Module Revamp. | 2026-09-04 | Server | 2026-09-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1495 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Nithin B P10(BE), Sreedhar Patti P12(BE)
HKS | FIX:- error occurs when uploading a manpower distribution file without providing Vendor Code | 2026-09-04 | Admin Panel | 2026-09-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/650 | Mahima Jassi P1 (Product), "Amogh Nath P24(FE,BE)"
Generic | Temp Allow AY20 student bus mapping to AY21 renewed students. Allow AY20 AY21 students to raise parent concerns. Event Gallery fix | 2026-09-04 | Server | 2026-09-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1560 | Sanjay Madari P9(BE)
Bus Tracking | Node version upgrade: 24.14.1 and package upgrades Update the NC components and composables from `new admin panel` to `ntrack_web`. Code refactoring a few minor fixes. | 2026-09-04 | Web App | 2026-09-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/ntrack_web/-/merge_requests/49 | B Mouli P18 (FE)
HKS | enh: Include state info in HkS analytics export | 2026-10-04 | Server | 2026-10-04 | 2026-10-04 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1563 | Mahima Jassi P1 (Product), Nihal B P11(BE), Sanjay Madari P9(BE)
L&D | Update on minimum time duration watched for drm videos. | 4/13/2026 | Web App | 4/13/2026 | 4/13/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_lnd_web/-/merge_requests/83 | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Manisha Shankarlal Sachdeo P23(FE)
Adoption Calling | ( Adoption calling ay21 student info ) | 4/14/2026 | Server | 4/14/2026 | 4/15/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1564 | Chidananda Sahu P13 (BE)
Re-Design | Enhancement: Excel Bulk Upload composable & Fix Table Button Visuals. | 4/14/2026 | Admin Panel | 4/14/2026 | 4/15/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/655 | Rachamalla Sai Ram Reddy P27(FE), Aditya Singh P22(FE)
Generic | Fix: Update health check endpoint to /api/health | 4/14/2026 | Server | 4/14/2026 | 4/15/2026 |  | https://git.narayanagroup.com/nconnect/ntrack_server/-/merge_requests/43 | Sanjay Madari P9(BE), "Amogh Nath P24(FE,BE)"
Attendance | Refactor Student Attendance module Excel Reports to Use SpreadCheetah Source Generator | 4/15/2026 | Server | 4/15/2026 | 4/15/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1253 | Nithin B P10(BE), Nihal B P11(BE), Suresh Gundupalli P15 (BE)
nTrack | Gps reports issue fixes | 4/15/2026 | Server | 4/15/2026 | 4/15/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1562 https://git.narayanagroup.com/nconnect/ntrack_server/-/merge_requests/42 | Sanjay Madari P9(BE), Nihal B P11(BE)
Parent Concerns | parent concern enhancements | 4/16/2026 | Admin Panel | 4/16/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/606 | Rachamalla Sai Ram Reddy P27(FE), Mrinmoyee Banerjee P6(Product Designer), Harshini Bollineni P21 (FE), G Lakshmi Priyanka P3(QA)
Parent Concerns | parent concern enhancements | 4/16/2026 | Server | 4/16/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1503 | Mrinmoyee Banerjee P6(Product Designer), Sreedhar Patti P12(BE), G Lakshmi Priyanka P3(QA)
nScribeAI | Enhancement: nScribe AI Default Month Filter | 4/17/2026 | Admin Panel | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/659 | Rachamalla Sai Ram Reddy P27(FE), Sriramula Prathyusha P20 (FE), M Gaurav Dhir P2(product), G Lakshmi Priyanka P3(QA)
nScribeAI | Enhancement: nScribe AI Default Month Filter | 4/17/2026 | Server | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1566/diffs | M Gaurav Dhir P2(product), G Lakshmi Priyanka P3(QA), Nithin B P10(BE)
HKS | HkS Capture and Quota Percentages Addition | 4/17/2026 | Server | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1561 | "Amogh Nath P24(FE,BE)", Mahima Jassi P1 (Product), Santosh Sankanal P4(QA)
HKS | Staff attendance export dropdown and inline percentages | 4/17/2026 | Admin Panel | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/656 | "Amogh Nath P24(FE,BE)", Mahima Jassi P1 (Product), Santosh Sankanal P4(QA)
HKS | enh: Added filters in Hks Dashboard and Pie chart APIs | 4/17/2026 | Server | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1570 | "Amogh Nath P24(FE,BE)", Santosh Sankanal P4(QA), Mahima Jassi P1 (Product)
HKS | Forward team leader and related filters to HkS dashboard and graph APIs | 4/17/2026 | Admin Panel | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/662 | "Amogh Nath P24(FE,BE)", Santosh Sankanal P4(QA), Mahima Jassi P1 (Product)
MicroSchedule Analytics | MicroSchedule analytics | 4/17/2026 | Server | 4/17/2026 | 4/17/2026 | MS Analytics Previously, MicroSchedule analytics were not working properly. Phase 1: Fixed and validated core reports: Submission analysis Approval analytics Section-wise export Teacher-wise, branch-wise, and subject-wise data | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1390 | Nithin B P10(BE), Chidananda Sahu P13 (BE), Nihal B P11(BE)
MicroSchedule Analytics | MicroSchedule analytics | 4/17/2026 | Admin Panel | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/646 | Rachamalla Sai Ram Reddy P27(FE), "Amogh Nath P24(FE,BE)"
Announcement | Announcement Comment-reply deletion update. | 4/17/2026 | Server | 4/17/2026 | 4/17/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1576 | Mahima Jassi P1 (Product), Sreedhar Patti P12(BE), Sanjay Madari P9(BE)
HKS | Enh: Adds AGM and Team Leader filter support to the Feedback Forms admin page | 4/18/2026 | Admin Panel | 4/18/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/661 | Mahima Jassi P1 (Product), "Amogh Nath P24(FE,BE)"
HKS | feedback forms staff app changes | 4/18/2026 | Server | 4/18/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1525 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Nihal B P11(BE)
Bus Tracking | fix: Bus tracking bulk student mapping issue | 4/20/2026 | Server | 4/20/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1578 | Sanjay Madari P9(BE), Nihal B P11(BE)
HKS | feedback forms admin panel changes | 4/20/2026 | Server | 4/20/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1567 | Sanjay Madari P9(BE), Nihal B P11(BE), Mahima Jassi P1 (Product)
HKS | feedback forms admin panel changes | 4/20/2026 | Admin Panel | 4/20/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/661 | Mahima Jassi P1 (Product), "Amogh Nath P24(FE,BE)"
Re-Design | redesign component changes | 4/20/2026 | Admin Panel | 4/20/2026 | 4/21/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/658 | Rachamalla Sai Ram Reddy P27(FE), Harshini Bollineni P21 (FE)
Adoption Calling | doption calling call status issue fix. | 4/21/2026 | Server | 4/21/2026 | 4/22/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1569 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), Sreedhar Patti P12(BE)
Generic | Unnecessary imports removal in new admin repo | 4/21/2026 | Admin Panel | 4/21/2026 | 4/22/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/668 | Rachamalla Sai Ram Reddy P27(FE), Harshini Bollineni P21 (FE)
Generic | Instant Parent Logout when did_logout set as true. | 4/21/2026 | Server | 4/21/2026 | 4/22/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1583/diffs | Sanjay Madari P9(BE)
Micro Schedule | MS Section Master Student Count Optimization. | 4/21/2026 | Server | 4/21/2026 | 4/22/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1455 | Sreedhar Patti P12(BE)
Attendance | Class Attendance Percentage conversion issue | 4/22/2026 | Server | 4/22/2026 | 4/22/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1584 | Sanjay Madari P9(BE)
Bus Tracking | Enh: Bus Tracking added fields in Reports. | 4/23/2026 | Server | 4/23/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1575 | Sanjay Madari P9(BE), Sreedhar Patti P12(BE)
Session Logout | Staff App session sign out from admin panel feature | 4/23/2026 | Admin Panel | 4/23/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin/-/merge_requests/596 | Rachamalla Sai Ram Reddy P27(FE), Mahima Jassi P1 (Product), Harshini Bollineni P21 (FE), Santosh Sankanal P4(QA)
Session Logout | Staff App session sign out from admin panel feature | 4/23/2026 | Server | 4/23/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1529 | Sanjay Madari P9(BE), Premchand Kodali P14 (BE), Santosh Sankanal P4(QA)
Parent Check-In | ix and designation hierarchy inclusion in Parent check-in module | 4/23/2026 | Server | 4/23/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1565 | Mahima Jassi P1 (Product), Sanjay Madari P9(BE), G Lakshmi Priyanka P3(QA), Premchand Kodali P14 (BE)
HKS | Hks consolidated report enhancement | 4/27/2026 | Server | 4/27/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1585 | Mahima Jassi P1 (Product), Nithin B P10(BE), Santosh Sankanal P4(QA), Nihal B P11(BE)
HKS | enh: Skip Redis location queue push when DeviceTime is null | 4/27/2026 | Server | 4/27/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/ntrack_server/-/merge_requests/44 | Sanjay Madari P9(BE), Nihal B P11(BE)
Re-Design | Enhancement: New Components and variant support for existing components | 4/28/2026 | Admin Panel | 4/28/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/556/ | Rachamalla Sai Ram Reddy P27(FE), G Lakshmi Priyanka P3(QA), Harshini Bollineni P21 (FE), Ayushmaan Roy P25(FE), Manisha Shankarlal Sachdeo P23(FE)
Micro Schedule | MR for microschedule enhancements | 4/29/2026 | Admin Panel | 4/29/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/681 | Rachamalla Sai Ram Reddy P27(FE), Sriramula Prathyusha P20 (FE), G Lakshmi Priyanka P3(QA)
DIsha | Sub: API/UI Enhancements and Fixes For Both Student and Admin Parts of Disha AI. Postgres Migration On Backend Part. | 4/29/2026 | Web App | 4/29/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/rag_disha/-/merge_requests/1 | Nithin B P10(BE), Mrinmoyee Banerjee P6(Product Designer), Premchand Kodali P14 (BE)
Re-Design | Fix: NcPagination page clamp on page size change and state filter issue. | 4/30/2026 | Admin Panel | 4/30/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_admin_new/-/merge_requests/615 | Rachamalla Sai Ram Reddy P27(FE), Aditya Singh P22(FE), Santosh Sankanal P4(QA)
Re-Design | Fix: NcPagination page clamp on page size change and state filter issue. | 4/30/2026 | Server | 4/30/2026 | 2026-07-05 |  | https://git.narayanagroup.com/nconnect/nconnect_server/-/merge_requests/1523 | Nithin B P10(BE), Santosh Sankanal P4(QA)
Flutter Version Updates | Parent APP | 2026-06-04 | Flutter | 2026-06-04 | 4/16/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/412 | Medagone Ranadeep P17 (Flutter), G Lakshmi Priyanka P3(QA)
Flutter Version Updates | Staff App | 2026-06-04 | Flutter | 2026-06-04 | 4/16/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/221 | G Lakshmi Priyanka P3(QA), Medagone Ranadeep P17 (Flutter)
Announcement | Parent app announcement comment text fix: | 2026-06-04 | Flutter | 2026-06-04 | 4/16/2026 | Parent app changelog: Added comment feature to announcements along with improved UI/UX for smoother functionality and a better user experience. Addressed reported issues and resolved known defects. General stability enhancements and optimized app performance. | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/222 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Medagone Ranadeep P17 (Flutter)
Announcement | Staff app announcement revamp: | 2026-06-04 | Flutter | 2026-06-04 | 4/16/2026 | Added announcement creation feature along with improved UI/UX and enhanced functionality for a better user experience. Enhanced feedback forms with new features and optimizations to improve usability and performance. Added a redirection icon to the 'Received' tag in the parent check-in call history table to allow feedback review. Addressed reported issues and resolved known defects. General stability enhancements and optimized app performance. | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/394 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Medagone Ranadeep P17 (Flutter)
Announcement | Staff app announcement notification redirection and minor bug fixes | 2026-09-04 | Flutter | 2026-09-04 | 4/16/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/414 | Mahima Jassi P1 (Product), Santosh Sankanal P4(QA), Medagone Ranadeep P17 (Flutter)
Announcement | photo video permissions | 4/16/2026 | Flutter | 4/16/2026 | 4/16/2026 |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/225 | Medagone Ranadeep P17 (Flutter)
Generic | Staff App Google console warnings fixes | 4/27/2026 | Flutter | 4/27/2026 |  |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/417 | Medagone Ranadeep P17 (Flutter)
Generic | Parent App Google console warnings fixes | 4/27/2026 | Flutter | 4/27/2026 |  |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/228 | Medagone Ranadeep P17 (Flutter)
Exam Results | Parent app exam results | 4/27/2026 | Flutter | 4/27/2026 |  | Date filter fix. Previous exams exam type filters issue fix Shimmer fix in previous list screen Hidding rank if the rank is coming null Code refactoring | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/226 | Medagone Ranadeep P17 (Flutter), G Lakshmi Priyanka P3(QA), Sanjay Madari P9(BE)
Package Upgrades | Parent App | 4/28/2026 | Flutter | 4/28/2026 |  |  | https://git.narayanagroup.com/nconnect/nconnect_parent/-/merge_requests/230 | Madari Ravalika P19(Flutter), Medagone Ranadeep P17 (Flutter)
Package Upgrades | Staff App | 4/28/2026 | Flutter | 4/28/2026 |  |  | https://git.narayanagroup.com/nconnect/nconnect_staff/-/merge_requests/419 | Madari Ravalika P19(Flutter), Medagone Ranadeep P17 (Flutter)